## Launch Plan
Milk-Based Beverage Launch - Project Timeline
Target launch: 9/30/2026 ¦ Required start: 6/15/2026 ¦ ~15 weeks
Project lead: you (PM) drive & manage every task, all phases. Deliverable owner: the client lead. "Executed by" = the function doing the work under your coordination.
Phase | Task | Executed by (function) | Start | End | Lead | Dep | Crit | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
[8 empty] | 6/15 | 6/22 | 6/29 | 7/6 | 7/13 | 7/20 | 7/27 | 8/3 | 8/10 | 8/17 | 8/24 | 8/31 | 9/7 | 9/14 | 9/21 | 9/28
Phase 1 - Validation | Product validation: 4-gallon test + lab / process authority | R&D + Quality | 6/15 | 7/12 | 4 wk | - | Yes | bar: 6/15 to 7/6
Phase 2 - Trial | Confirm & approve artwork (cartons + labels) | Creative / Brand | 7/6 | 7/12 | 1 wk | - | bar: 7/6
Phase 2 - Trial | Order trial CANS (long-lead) | Procurement | 7/13 | 8/9 | 4 wk | T1 | Yes | bar: 7/13 to 8/3
Phase 2 - Trial | Order trial CARTONS (long-lead) | Procurement | 7/13 | 8/9 | 4 wk | T2 | bar: 7/13 to 8/3
Phase 2 - Trial | Order trial INGREDIENTS | Procurement | 7/20 | 8/9 | 3 wk | T1 | bar: 7/20 to 8/3
Phase 2 - Trial | Order trial LABELS | Procurement | 7/27 | 8/9 | 2 wk | T2 | bar: 7/27 to 8/3
Phase 2 - Trial | Trial production run (2,400 cans) | Production | 8/10 | 8/16 | 1 wk | T3-T6 | Yes | bar: 8/10
Phase 2 - Trial | Secure trial approval (lab / process authority) | Quality / Reg. | 8/17 | 8/23 | 1 wk | T7 | Yes | bar: 8/17
Phase 3 - Full Run | Implement trial learnings | R&D | 8/24 | 9/6 | 2 wk | T8 | bar: 8/24 to 8/31
Phase 3 - Full Run | Order full-run CANS (long-lead) | Procurement | 8/24 | 9/20 | 4 wk | T8 | Yes | bar: 8/24 to 9/14
Phase 3 - Full Run | Order full-run INGREDIENTS | Procurement | 8/31 | 9/20 | 3 wk | T8 | bar: 8/31 to 9/14
Phase 3 - Full Run | Order full-run LABELS | Procurement | 9/7 | 9/20 | 2 wk | T8 | bar: 9/7 to 9/14
Phase 3 - Full Run | Align with co-packer on scheduling | Production | 8/31 | 9/20 | 3 wk | T8 | bar: 8/31 to 9/14
Phase 3 - Full Run | Final production run (400,000 cans) | Production | 9/21 | 9/27 | 1 wk | T9-T13 | Yes | bar: 9/21
Milestone | LAUNCH (9/30) | Marketing | 9/28 | 10/4 | - | T14 | Yes | bar: 9/28
PM | Coordinate, track & drive all tasks + weekly status
Legend: | Critical path | Non-critical | PM coord. | ★ Launch
How I would manage this project (Key Ask)
Critical path: T1 Validation -> T3 Trial cans (4wk) -> T7 Trial run -> T8 Trial approval -> T10 Full-run cans (4wk) -> T14 Final run -> Launch.
Approach: order long-lead cans/cartons first and in parallel; overlap artwork approval with validation; run full-run can procurement inside the mandatory 4-week trial-approval gap; weekly status against the critical path; escalate early on the approval gate and co-packer.
Risks & the one item to confirm
- Long-lead cans / cartons are the top schedule risk; a supplier slip pushes the launch.
- The 4-week trial-approval gate is fixed; the plan has little slack, so a failed validation or trial likely misses 9/30.
- Co-packer availability for the final run is a hard dependency.
- CONFIRM: the brief lists cartons only for the trial, not the full run - add a 4-week carton lead to Phase 3 if full-run cartons are needed.